## Slide 1
Session # 10
Project Risk Management

## Slide 2: Learning Objectives
Explain the concept of risk as it relates to project management, and list the advantages of managing project risks according to best practices
Discuss the elements of planning risk management and the contents of a risk management plan
List common sources of risks on information technology (IT) projects
Describe the process of identifying risks and create a risk register and risk report
Discuss qualitative risk analysis and explain how to calculate risk factors, create probability/impact matrixes, and apply the Top Ten Risk Item Tracking technique to rank risks

## Slide 3: Learning Objectives
Explain quantitative risk analysis and how to apply decision trees, simulation, and sensitivity analysis to quantify risks
Provide examples of using different risk response planning strategies to address both negative and positive risks
Discuss how to monitor risks
Describe how software can assist in project risk management
Discuss considerations for agile/adaptive environments

## Slide 4: The Importance of Project Risk Management
Project risk management is the art and science of identifying, analyzing, and responding to risk throughout the life of a project and in the best interests of meeting project objectives
  Risk management is often overlooked in projects, but it can help improve project success by helping select good projects, determining project scope, and developing realistic estimates

## Slide 5: The Importance of Project Risk Management
Research shows a need to improve project risk management
  Study by Ibbs and Kwak shows risk management has the lowest maturity rating of all knowledge areas
  A similar survey was completed with software development companies in Mauritius, South Africa, and risk management also had the lowest maturity
  KLCI study shows the benefits of following good software risk management practices

## Slide 6: The Importance of Project Risk Management

## Slide 7: Global Issues
Many people around the world suffered from financial losses as various financial markets dropped in the fall of 2008, even after the $700 billion bailout bill was passed by the U.S. Congress
  According to a global survey of 316 financial services executives, over 70 percent of respondents believed that the losses stemming from the credit crisis were largely due to failures to address risk management issues
Worldwide banking and insurance sectors will spend about $78.6 billion on risk information technologies and services in 2015, growing to $96.3 billion by 2018

## Slide 8: The Importance of Project Risk Management
A dictionary definition of risk is “the possibility of loss or injury”
  General definition of a project risk: an uncertainty that can have a negative or positive effect on meeting project objectives
  Managing negative risks involves a number of possible actions that project managers can take to avoid, lessen, change, or accept the potential effects of risks on their projects
  Positive risk management is like investing in opportunities

## Slide 9: Best Practice
Some organizations make the mistake of only addressing tactical and negative risks when performing project risk management
  David Hillson suggests overcoming this problem by widening the scope of risk management to encompass both strategic risks and upside opportunities, which he refers to as integrated risk management
  Hillson described the importance of good working relationships; especially between the project sponsor and project manager

## Slide 10: The Importance of Project Risk Management
Risk utility is the amount of satisfaction or pleasure received from a potential payoff
  Utility rises at a decreasing rate for people who are risk-averse
  Those who are risk-seeking have a higher tolerance for risk and their satisfaction increases when more payoff is at stake
  Risk-neutral approach achieves a balance between risk and payoff

## Slide 11: The Importance of Project Risk Management

## Slide 12: Advice for Young Professionals
Young project professionals are sometimes more willing to take risks with unique or untested approaches
  Take the time to find out what other, more experienced people might feel about the circumstances of a project before making up your mind about potential risks
    Then, taking other views into account, you can determine how best to plan for the impacts that might occur while balancing the rewards of a potential payoff from a unique or untested approach

## Slide 13: The Importance of Project Risk Management
Project risk management processes
  Planning risk management: deciding how to approach and plan the risk management activities for the project
  Identifying risks: determining which risks are likely to affect a project and documenting the characteristics of each
  Performing qualitative risk analysis: prioritizing risks based on their probability and impact of occurrence
  Performing quantitative risk analysis: numerically estimating the effects of risks on project objectives
  Planning risk responses: taking steps to enhance opportunities and reduce threats to meeting project objectives
  Implementing risk responses: implementing the risk response plans
  Monitoring risk: monitoring identified and residual risks, identifying new risks, carrying out risk response plans, and evaluating the effectiveness of risk strategies throughout the life of the project

## Slide 14: Planning Risk Management
Main output of this process is a risk management plan
  Documents the procedures for managing risk throughout a project
The project team should review project documents as well as corporate risk management policies, risk categories, lessons-learned reports from past projects, and templates for creating a risk management plan
  It is also important to review the risk tolerances of various stakeholders

## Slide 15: Planning Risk Management
Additional plans
  Contingency plans: predefined actions that the project team will take if an identified risk event occurs
  Fallback plans: developed for risks that have a high impact on meeting project objectives, and are put into effect if attempts to reduce the risk are not effective
  Contingency reserves or allowances: funds included in the cost baseline that can be used to mitigate cost or schedule overruns if known risks occur
  Management reserves: funds held for unknown risks that are used for management control purposes

## Slide 16: Planning Risk Management
Topic | Questions to Answer
Methodology | How will risk management be performed on this project? What tools and data sources are available and applicable?
Roles and responsibilities | Which people are responsible for implementing specific tasks and providing deliverables related to risk management?
Budget and schedule | What are the estimated costs and schedules for performing risk-related activities?
Risk categories | What are the main categories of risks that should be addressed on this project? Is there a risk breakdown structure for the project? (See the information on risk breakdown structures later in this chapter.)
Risk probability and impact | How will the probabilities and impacts of risk items be assessed? What scoring and interpretation methods will be used for the qualitative and quantitative analysis of risks? How will the probability and impact matrix be developed?
Revised stakeholders’ tolerances | Have stakeholders’ tolerances for risk changed? How will those changes affect the project?
Tracking | How will the team track risk management activities? How will lessons learned be documented and shared? How will risk management processes be audited?
Risk documentation | What reporting formats and processes will be used for risk management activities?
Topics addressed in a risk management plan

## Slide 17: Common Sources of Risk on IT Projects
Several studies show that IT projects share some common sources of risk
  The Standish Group developed an IT success potential scoring sheet based on potential risks
Other broad categories of risk help identify potential risks
  Market risk
  Financial risk
  Technology risk
  People risk
  Structure/process risk
A risk breakdown structure is a hierarchy of potential risk categories for a project

## Slide 18: Common Sources of Risk on IT Projects

## Slide 19: Common Sources of Risk on IT Projects
Knowledge Area | Risk Conditions
Integration | Inadequate planning; poor resource allocation; poor integration management; lack of post-project review
Scope | Poor definition of scope or work packages; incomplete definition
Time | Errors in estimating time or resource availability; errors in determining the critical path; poor allocation and management of float; early release of competitive products
Cost | Estimating errors; inadequate productivity, cost, change, or contingency
Quality | Poor attitude toward quality; substandard design, materials, and workmanship; inadequate quality assurance program
Human resource | Poor conflict management; poor project organization and definition of responsibilities; absence of leadership
Communications | Carelessness in planning or communicating
Risk | Ignoring risk; unclear analysis of risk; poor insurance management
Procurement | Unenforceable conditions or contract clauses; adversarial relations
Stakeholders | Lack of consultation with key stakeholder; poor sponsor engagement
Potential negative risk conditions associated with each knowledge area. *Source: R.M. Wideman

## Slide 20: What Went Wrong?
In a 2013 survey, risk management was a high priority
  However, only 66 percent of companies said they often build it into their strategy planning decisions
Airline incidents cause concerns, especially when lives are lot
  The 2015 Germanwings crash resulted in 150 deaths, allegedly due to the co-pilot’s poor mental state
  They responded immediately by implementing a rule that two people must be in the cockpit at all times and are considering changes to medical and psychological tests for pilots

## Slide 21: Identifying Risks
Understanding what potential events might hurt or enhance a particular project
  You cannot manage risks if you do not identify them first
Another consideration is the likelihood of advanced discovery
  Often viewed at a program level rather than a project level
Suggestions for identifying risks: tools and techniques
  Brainstorming
  The Delphi Technique
  Interviewing
  SWOT analysis

## Slide 22: Identifying Risks
Brainstorming
  Group attempts to generate ideas or find a solution for a specific problem by amassing ideas spontaneously and without judgment
  An experienced facilitator should run the brainstorming session
  Be careful not to overuse or misuse brainstorming
    Psychology literature shows that individuals produce a greater number of ideas working alone than they do through brainstorming in small, face-to-face groups
    Group effects often inhibit idea generation

## Slide 23: Identifying Risks
Delphi Technique
  Used to derive a consensus among a panel of experts who make predictions about future developments
  Provides independent and anonymous input regarding future events
  Uses repeated rounds of questioning and written responses and avoids the biasing effects possible in oral methods

## Slide 24: Identifying Risks
Interviewing
  Fact-finding technique for collecting information in face-to-face, phone, e-mail, or virtual discussions
  Interviewing people with similar project experience is an important tool for identifying potential risks

## Slide 25: Identifying Risks
SWOT analysis
  Strengths, weaknesses, opportunities, and threats
  Helps identify the broad negative and positive risks that apply to a project

## Slide 26: The Risk Register
Important output of the risk identification process
  List of identified risks and other information needed to begin creating a risk register
    Contains the results of various risk management processes and that is often displayed in a table or spreadsheet format
    Tool for documenting potential risk events and related information
  Risk events refer to specific, uncertain events that may occur to the detriment or enhancement of the project

## Slide 27: Risk register contents
  Identification number for each risk event
  Rank for each risk event
  Name of each risk event
  Description of each risk event
  Category under which each risk event falls
  Root cause of each risk
  Triggers for each risk; indicators or symptoms of actual risk events
  Potential responses to each risk
  Risk owner or person who will own or take responsibility for each risk
  Probability and impact of each risk occurring
  Status of each risk

## Slide 28: Sample Risk Register
No. | Rank | Risk | Description | Category | Root Cause | Triggers | Potential Responses | Risk Owner | Probability | Impact | Status
R44 | 1 |  |  |  |  |  |  |  |  |  | 
R21 | 2 |  |  |  |  |  |  |  |  |  | 
R7 | 3 |  |  |  |  |  |  |  |  |  | 

## Slide 29: The Risk Register
Risk report contents
  Sources of overall project risk
  Important drivers of overall project risk exposure
  Summary information on risk events

## Slide 30: Performing Qualitative Risk Analysis
Assess the likelihood and impact of identified risks to determine their magnitude and priority
Risk quantification tools and techniques
  Probability/impact matrixes
  The Top Ten Risk Item Tracking
  Expert judgment

## Slide 31: Using Probability/Impact Matrixes to Calculate Risk Factors
Lists relative probability of a risk occurring on one side of a matrix or axis on a chart and the relative impact of the risk occurring
  List the risks and then label each one as high, medium, or low in terms of its probability of occurrence and its impact if it did occur
Calculates risk factors
  Numbers that represent the overall risk of specific events based on their probability of occurring and the consequences to the project if they do occur

## Slide 32: Using Probability/Impact Matrixes to Calculate Risk Factors

## Slide 33: Probability/Impact Matrix
 |  | Impact |  |  |  | 
 |  | Trivial | Minor | Moderate | Major | Extreme
Probability | Rare | Low | Low | Low | Medium | Medium
 | Unlikely | Low | Low | Medium | Medium | Medium
 | Moderate | Low | Medium | Medium | Medium | High
 | Likely | Medium | Medium | Medium | High | High
 | Very Likely | Medium | Medium | High | High | High

## Slide 34: Probability/Impact Matrix
Adopted from PMI’s PMBOK® Guide

## Slide 35: Using Probability/Impact Matrixes to Calculate Risk Factors

## Slide 36: Top Ten Risk Item Tracking
Qualitative risk analysis tool that helps to identify risks and maintain an awareness of risks throughout the life of a project
  Involves establishing a periodic review of the top ten project risk items
  Includes the current ranking, previous ranking, number of times the risk appears on the list over a period of time, and a summary of progress made in resolving the risk item
A watch list is a list of risks that are low priority, but are still identified as potential risks
  Qualitative analysis can also identify risks that should be evaluated quantitatively

## Slide 37: Top Ten Risk Item Tracking
 | Monthly Ranking | Monthly Ranking | Monthly Ranking | 
Risk Event | Rank This Month | Rank Last Month | Number of Months in Top Ten | Risk Resolution Progress
Inadequate planning | 1 | 2 | 4 | Working on revising the entire project management plan
Poor definition | 2 | 3 | 3 | Holding meetings with project customer and sponsor to clarify scope
Absence of leadership | 3 | 1 | 2 | Assigned a new project manager to lead the project after the previous one quit
Poor cost estimates | 4 | 4 | 3 | Revising cost estimates
Poor time estimates | 5 | 5 | 3 | Revising schedule estimates
Example of top ten risk item tracking

## Slide 38: Media Snapshot
The story of the Titanic is known throughout the world, and on April 15, 2012, people acknowledged the anniversary of the Titanic’s sinking
  A recent article in PMI’s Virtual Library explains how to avoid “the Titanic factor” in your projects by analyzing the interdependence of risks
    For example, the probability of one risk event occurring might change if another one materializes, and the response to one risk event might affect another

## Slide 39: Performing Quantitative Risk Analysis
Often follows qualitative risk analysis, but both can be done together
  Large, complex projects involving leading edge technologies often require extensive quantitative risk analysis
Main techniques
  Decision tree analysis
  Simulation
  Sensitivity analysis

## Slide 40: Decision Trees and Expected Monetary Value (EMV)
A decision tree is a diagramming analysis technique used to help select the best course of action in situations in which future outcomes are uncertain
  Estimated monetary value (EMV) is the product of a risk event probability and the risk event’s monetary value
    You can draw a decision tree to help find the EMV

## Slide 41: Decision Trees and Expected Monetary Value (EMV)

## Slide 42: Simulation
Uses a representation or model of a system to analyze the expected behavior or performance of the system
  Monte Carlo analysis simulates a model’s outcome many times to provide a statistical distribution of the calculated results
    Predict the probability of finishing by a certain date or the probability that the cost will be equal to or less than a certain value
    You can use several different types of distribution functions when performing a Monte Carlo analysis

## Slide 43: Simulation
Steps of a Monte Carlo analysis
  Collect the most likely, optimistic, and pessimistic estimates for the variables in the model
  Determine the probability distribution of each variable
  Select a random value based on the probability distribution for each variable
  Run a deterministic analysis or one pass through the model
  Repeat steps three and four many times to obtain the probability distribution of the model’s results

## Slide 44: Simulation

## Slide 45: What Went Right?
Microsoft Excel is a common tool for performing quantitative risk analysis
  General Motors uses simulation for forecasting its net income, predicting structural costs and purchasing costs of vehicles, and determining the company’s susceptibility to different kinds of risk
  Eli Lilly uses simulation to determine the optimal plant capacity that should be built for developing each drug
  Procter & Gamble uses simulation to model foreign exchange risk
Monte Carlo simulation can also help reduce schedule risk on agile projects

## Slide 46: Sensitivity Analysis
Used to show the effects of changing one or more variables on an outcome
  For example, many people use it to determine what the monthly payments for a loan will be given different interest rates or periods of the loan
Spreadsheet software, such as Microsoft Excel, is a common tool for performing sensitivity analysis

## Slide 47: Sensitivity Analysis

## Slide 48: Planning Risk Responses
After identifying and quantifying risks, the organization must decide how to respond to them
  Basic response strategies for negative risks
    Risk avoidance
    Risk acceptance
    Risk transference
    Risk mitigation
    Risk escalation
  Basic response strategies for positive risks
    Risk exploitation
    Risk sharing
    Risk enhancement
    Risk acceptance
    Risk escalation

## Slide 49: Planning Risk Responses
Technical Risks | Cost Risks | Schedule Risks
Emphasize team support and avoid stand-alone project structure | Increase the frequency of project monitoring | Increase the frequency of project monitoring
Increase project manager authority | Use WBS and CPM | Use WBS and CPM
Improve problem handling and communication | Improve communication, understanding of project goals, and team support | Select the most experienced project manager
Increase the frequency of project monitoring | Increase project manager authority | 
Use WBS and CPM |  | 
General risk mitigation strategies for technical, cost, and schedule risks. *Source: J. Couillard

## Slide 50: Planning Risk Responses
It’s also important to identify residual and secondary risks
  Residual risks: risks that remain after all of the response strategies have been implemented
  Secondary risks: direct result of implementing a risk response

## Slide 51: Implementing Risk Responses
Main executing process performed as part of project risk management is implementing risk responses
  Key outputs
    Change requests
    Project documents updates

## Slide 52: Monitoring Risks
Involves ensuring the appropriate risk responses are performed, tracking identified risks, identifying and analyzing new risk, and evaluating effectiveness of risk management throughout the entire project
  Project risk management does not stop with the initial risk analysis
Carrying out individual risk management plans involves monitoring risks based on defined milestones and making decisions regarding risks and their response strategies
  Project teams sometimes use workarounds—unplanned responses to risk events—when they do not have contingency plans in place

## Slide 53: Using Software to Assist in Project Risk Management
Risk registers can be created in a simple Microsoft Word or Excel file or as part of a sophisticated database
  More sophisticated risk management software, such as Monte Carlo simulation tools, help develop models and use simulations to analyze and respond to various risks

## Slide 54: Considerations for Agile/Adaptive Environments
All types of projects should share knowledge related to risks as quickly as possible and keep documents up to date
  Risk is considered during each iteration for agile/adaptive projects, which does elevate its importance
  Changing priorities can be addressed more easily by changing the product backlog for each iteration

## Slide 55: Chapter Summary
Risk is an uncertainty that can have a negative or positive effect on meeting project objectives
  Many organizations do a poor job of project risk management, if they do any at all
  Successful organizations realize the value of good project risk management
Risk management is an investment
  Costs are associated with identifying risks, analyzing those risks, and establishing plans to address them
Implementing risk responses involves putting the appropriate risk response plans into action
  Monitoring risks involves monitoring implementation of risk response plans, tracking identified risks, identifying and analyzing new risks, and evaluating effectiveness of risk management throughout the entire project